## Project Summary
Notable - AI Meeting-to-Task Scheduler
Project Todo List
Category | Total Tasks | Estimated Hours
Project Setup & Infrastructure | 20 | 119
Database & Storage | 15 | 94
Backend APIs | 35 | 270
LLM & Extraction | 30 | 256
Workers & Queue | 24 | 218
Scheduling Algorithm | 25 | 238
Integrations | 30 | 218
Frontend Development | 60 | 554
Testing | 32 | 378
Analytics & Monitoring | 20 | 134
Security & Compliance | 25 | 224
Documentation | 23 | 230
Deployment & DevOps | 23 | 196
Optimization | 14 | 158
Launch Preparation | 20 | 428
Future Enhancements | 25 | 1575
TOTAL | 0 | 5290
Priority Breakdown
Priority | Count
Critical | ~80 tasks | Foundation and core features
High | ~250 tasks | Essential features and integrations
Medium | ~80 tasks | Important enhancements
Low | ~30 tasks | Nice-to-have features

## 1. Setup & Database
Phase | Task ID | Task Name | Description | Owner/Team | Priority | Estimated Hours | Dependencies | Status | Notes
PROJECT SETUP
Project Initialization | SETUP-001 | Initialize Git repository | Create Git repo with proper .gitignore for Node/Python, add README.md, LICENSE, and initial commit | DevOps | High | 1 |  | Not Started | Use .gitignore templates for Node.js and Python
Project Initialization | SETUP-002 | Set up project directory structure | Create folder structure: /frontend, /backend, /workers, /database, /docs, /scripts, /tests | DevOps | High | 2 | SETUP-001 | Not Started | Follow microservices organization
Project Initialization | SETUP-003 | Define monorepo vs. multi-repo strategy | Decide whether to use monorepo (Nx, Turborepo) or separate repos for frontend/backend | Tech Lead | High | 4 | SETUP-001 | Not Started | Consider team size and deployment complexity
Project Initialization | SETUP-004 | Create environment configuration templates | Set up .env.example files for all services with required variables documented | Backend Dev | High | 3 | SETUP-002 | Not Started | Include API keys, DB URLs, OAuth credentials
Project Initialization | SETUP-005 | Set up Docker development environment | Create Dockerfile for each service and docker-compose.yml for local development | DevOps | High | 8 | SETUP-002 | Not Started | Include DB, Redis, and all services
DEVELOPMENT TOOLS
Development Tools | SETUP-006 | Configure code formatting (Prettier) | Set up Prettier with shared config for frontend and backend | Frontend Dev | Medium | 2 | SETUP-001 | Not Started
Development Tools | SETUP-007 | Configure linting (ESLint/Pylint) | Set up ESLint for TypeScript/JavaScript and Pylint/Flake8 for Python | Backend Dev | Medium | 3 | SETUP-001 | Not Started
Development Tools | SETUP-008 | Set up pre-commit hooks (Husky) | Install Husky for Git hooks running linting and tests before commits | DevOps | Medium | 2 | SETUP-006, SETUP-007 | Not Started
Development Tools | SETUP-009 | Configure TypeScript for frontend | Set up tsconfig.json with strict mode and path aliases | Frontend Dev | High | 3 | SETUP-002 | Not Started | Enable strict null checks
Development Tools | SETUP-010 | Set up VS Code workspace settings | Create .vscode/settings.json with recommended extensions and settings | Tech Lead | Low | 1 | SETUP-001 | Not Started | Include Python, TypeScript, Docker extensions
CI/CD PIPELINE
CI/CD | SETUP-011 | Set up GitHub Actions workflows | Create workflows for: lint, test, build, deploy (staging), deploy (production) | DevOps | High | 12 | SETUP-001 | Not Started | Separate workflows for frontend and backend
CI/CD | SETUP-012 | Configure automated testing in CI | Set up test runners in CI pipeline with code coverage reporting | DevOps | High | 6 | SETUP-011 | Not Started | Target 80% coverage minimum
CI/CD | SETUP-013 | Set up staging environment | Create staging environment mirroring production for testing | DevOps | High | 16 | SETUP-011 | Not Started | Use same tech stack as production
CI/CD | SETUP-014 | Configure production deployment pipeline | Set up blue-green or rolling deployment strategy for zero-downtime | DevOps | High | 20 | SETUP-013 | Not Started | Include rollback capabilities
CI/CD | SETUP-015 | Set up environment secrets management | Configure GitHub Secrets or cloud secrets manager for API keys | DevOps | Critical | 4 | SETUP-011 | Not Started | Never commit secrets to repo
MONITORING & LOGGING
Monitoring | SETUP-016 | Set up application logging (Winston/Python logging) | Configure structured logging with log levels and rotation | Backend Dev | High | 6 | SETUP-002 | Not Started | Use JSON format for easier parsing
Monitoring | SETUP-017 | Configure error tracking (Sentry) | Set up Sentry for frontend and backend error monitoring | DevOps | High | 8 | SETUP-002 | Not Started | Include source maps for stack traces
Monitoring | SETUP-018 | Set up APM (Application Performance Monitoring) | Configure monitoring for API latency, throughput, error rates | DevOps | Medium | 10 | SETUP-013 | Not Started | Consider New Relic, DataDog, or Prometheus
Monitoring | SETUP-019 | Configure database query monitoring | Set up slow query logs and query performance tracking | Backend Dev | Medium | 4 | DB-004 | Not Started | Monitor queries >100ms
Monitoring | SETUP-020 | Set up uptime monitoring | Configure health checks and alerting for service downtime | DevOps | High | 4 | SETUP-013 | Not Started | Use UptimeRobot or similar
DATABASE DESIGN
Database Schema | DB-001 | Design database schema (ERD) | Create Entity-Relationship Diagram for users, transcripts, tasks, meetings, integrations | Backend Dev | Critical | 12 |  | Not Started | Include all relationships and constraints
Database Schema | DB-002 | Define Users table schema | Fields: id, email, name, timezone, created_at, updated_at, oauth_tokens (encrypted) | Backend Dev | Critical | 4 | DB-001 | Not Started | Use UUID for id
Database Schema | DB-003 | Define Transcripts table schema | Fields: id, user_id, title, text, word_count, source, status, created_at, metadata (JSON) | Backend Dev | Critical | 4 | DB-001 | Not Started | Index on user_id and created_at
Database Schema | DB-004 | Define Tasks table schema | Fields: id, transcript_id, title, description, owner_name, owner_user_id, due_date, confidence, scheduled_time, duration_minutes, status, created_at, updated_at | Backend Dev | Critical | 6 | DB-001 | Not Started | Index on transcript_id, owner_user_id, due_date
Database Schema | DB-005 | Define Integrations table schema | Fields: id, user_id, service (enum), access_token (encrypted), refresh_token (encrypted), expires_at, scopes, metadata, created_at | Backend Dev | Critical | 4 | DB-001 | Not Started | Encrypt all tokens at rest
Database Schema | DB-006 | Define Jobs/Queue table schema | Fields: id, user_id, job_type, status, payload, result, error, created_at, started_at, completed_at | Backend Dev | High | 4 | DB-001 | Not Started | For async job tracking
DATABASE SETUP
Database Setup | DB-007 | Set up PostgreSQL database | Create database instance with proper configuration for production workload | DevOps | Critical | 8 | DB-001 | Not Started | Configure connection pooling
Database Setup | DB-008 | Configure database migrations (Alembic/Prisma) | Set up migration tool with initial schema migration | Backend Dev | Critical | 8 | DB-007 | Not Started | Version control all migrations
Database Setup | DB-009 | Create database indexes | Add indexes on foreign keys, search fields, and frequently queried columns | Backend Dev | High | 6 | DB-008 | Not Started | Monitor index performance
Database Setup | DB-010 | Implement database backup strategy | Set up automated daily backups with retention policy | DevOps | Critical | 6 | DB-007 | Not Started | Test restore process monthly
Database Setup | DB-011 | Configure database connection pooling | Set up connection pool with appropriate size limits | Backend Dev | High | 4 | DB-007 | Not Started | Prevent connection exhaustion
Database Setup | DB-012 | Set up database read replicas | Configure read replicas for scaling read-heavy queries | DevOps | Medium | 12 | DB-007 | Not Started | For future scalability
STORAGE
Storage | DB-013 | Set up S3/Object Storage for media files | Configure S3 bucket for audio/video transcript files | DevOps | High | 6 |  | Not Started | Set lifecycle policies for cost optimization
Storage | DB-014 | Configure Redis for caching | Set up Redis instance for session storage and query caching | DevOps | High | 6 |  | Not Started | Configure eviction policy
Storage | DB-015 | Set up Redis for message queue | Configure Redis for job queue if using BullMQ | DevOps | High | 4 | DB-014 | Not Started | Or use RabbitMQ/SQS alternative

## 2. Backend APIs
Phase | Task ID | Task Name | Description | Owner/Team | Priority | Estimated Hours | Dependencies | Status | Notes
BACKEND FOUNDATION
Backend Setup | BE-001 | Initialize backend project (FastAPI/NestJS) | Set up project with framework, folder structure, and basic configuration | Backend Dev | Critical | 8 | SETUP-002 | Not Started | Decision: Python FastAPI vs Node NestJS
Backend Setup | BE-002 | Set up database ORM (SQLAlchemy/Prisma) | Configure ORM with database connection and model definitions | Backend Dev | Critical | 8 | BE-001, DB-008 | Not Started
Backend Setup | BE-003 | Implement database models | Create ORM models for all tables matching schema | Backend Dev | Critical | 12 | BE-002, DB-002 to DB-006 | Not Started | Include relationships and validators
Backend Setup | BE-004 | Set up API routing structure | Create route modules for: /auth, /transcripts, /tasks, /integrations, /users | Backend Dev | High | 6 | BE-001 | Not Started | Use router/controller pattern
Backend Setup | BE-005 | Implement request/response schemas | Define Pydantic models (FastAPI) or DTOs (NestJS) for all endpoints | Backend Dev | High | 12 | BE-004 | Not Started | Include validation rules
Backend Setup | BE-006 | Set up CORS configuration | Configure CORS to allow frontend domain requests | Backend Dev | High | 2 | BE-001 | Not Started | Restrict to specific origins in production
Backend Setup | BE-007 | Implement global error handling middleware | Create middleware for catching and formatting all errors | Backend Dev | High | 6 | BE-001 | Not Started | Return consistent error structure
Backend Setup | BE-008 | Set up request logging middleware | Log all incoming requests with timing and status codes | Backend Dev | Medium | 4 | BE-001, SETUP-016 | Not Started
AUTHENTICATION & AUTHORIZATION
Auth | BE-009 | Design authentication strategy | Choose between JWT, sessions, or token-based auth | Tech Lead | Critical | 6 |  | Not Started | Consider OAuth requirements
Auth | BE-010 | Implement user registration endpoint | POST /auth/register - create user account | Backend Dev | High | 8 | BE-009, BE-003 | Not Started | Email validation and password hashing
Auth | BE-011 | Implement login endpoint | POST /auth/login - authenticate user and return token/session | Backend Dev | High | 8 | BE-010 | Not Started | Rate limit login attempts
Auth | BE-012 | Implement logout endpoint | POST /auth/logout - invalidate token/session | Backend Dev | Medium | 4 | BE-011 | Not Started
Auth | BE-013 | Implement password reset flow | Endpoints for requesting and completing password reset | Backend Dev | Medium | 12 | BE-011 | Not Started | Use time-limited tokens
Auth | BE-014 | Create authentication middleware | Middleware to verify token/session on protected routes | Backend Dev | Critical | 8 | BE-011 | Not Started
Auth | BE-015 | Implement role-based access control (RBAC) | Add user roles and permission checking | Backend Dev | Medium | 10 | BE-014 | Not Started | For future admin features
Auth | BE-016 | Set up OAuth 2.0 flow for Google | Implement OAuth login with Google for calendar access | Backend Dev | Critical | 16 | BE-011 | Not Started | Request minimal scopes initially
Auth | BE-017 | Implement token refresh mechanism | Auto-refresh OAuth tokens before expiry | Backend Dev | High | 8 | BE-016 | Not Started | Store refresh tokens securely
TRANSCRIPT APIs
Transcript API | BE-018 | Implement POST /api/transcripts endpoint | Accept transcript upload, validate, save to DB, enqueue job | Backend Dev | Critical | 12 | BE-004, BE-014 | Not Started | Return 202 with job ID
Transcript API | BE-019 | Implement GET /api/transcripts endpoint | List user's transcripts with pagination | Backend Dev | High | 6 | BE-018 | Not Started | Default page size 20
Transcript API | BE-020 | Implement GET /api/transcripts/{id} endpoint | Retrieve single transcript details | Backend Dev | High | 4 | BE-018 | Not Started | Include task count
Transcript API | BE-021 | Implement DELETE /api/transcripts/{id} endpoint | Soft delete transcript and associated tasks | Backend Dev | Medium | 6 | BE-018 | Not Started | Cascade to tasks
Transcript API | BE-022 | Add transcript text validation | Validate max length, encoding, and content sanitization | Backend Dev | High | 4 | BE-018 | Not Started | Prevent injection attacks
Transcript API | BE-023 | Implement transcript search endpoint | GET /api/transcripts/search with title/content filtering | Backend Dev | Low | 8 | BE-019 | Not Started | Use full-text search
TASK APIs
Task API | BE-024 | Implement GET /api/transcripts/{id}/tasks endpoint | Retrieve all tasks for a transcript | Backend Dev | Critical | 6 | BE-018 | Not Started | Sort by confidence desc
Task API | BE-025 | Implement GET /api/tasks/{id} endpoint | Retrieve single task details | Backend Dev | High | 4 | BE-024 | Not Started
Task API | BE-026 | Implement PATCH /api/tasks/{id} endpoint | Update task fields (title, owner, due_date, etc.) | Backend Dev | Critical | 10 | BE-024 | Not Started | Validate date formats
Task API | BE-027 | Implement DELETE /api/tasks/{id} endpoint | Delete a task | Backend Dev | High | 4 | BE-024 | Not Started | Also remove calendar event if scheduled
Task API | BE-028 | Implement POST /api/schedule endpoint | Trigger scheduling for specified task IDs | Backend Dev | Critical | 12 | BE-024 | Not Started | Enqueue scheduling job
Task API | BE-029 | Implement GET /api/tasks endpoint | List all user's tasks with filters (status, due_date range) | Backend Dev | High | 8 | BE-024 | Not Started | Support pagination and sorting
Task API | BE-030 | Add bulk task operations endpoint | PATCH /api/tasks/bulk for batch updates | Backend Dev | Medium | 8 | BE-026 | Not Started | Accept/reject multiple tasks
INTEGRATION APIs
Integration API | BE-031 | Implement GET /api/integrations endpoint | List user's connected integrations | Backend Dev | High | 4 | BE-004 | Not Started | Mask sensitive tokens
Integration API | BE-032 | Implement POST /api/integrations/google endpoint | Complete Google OAuth flow and save tokens | Backend Dev | Critical | 12 | BE-016 | Not Started | Handle OAuth callback
Integration API | BE-033 | Implement DELETE /api/integrations/{service} endpoint | Disconnect integration and revoke tokens | Backend Dev | High | 6 | BE-031 | Not Started | Call provider revocation endpoint
Integration API | BE-034 | Implement POST /api/integrations/slack endpoint | Complete Slack OAuth flow | Backend Dev | High | 12 | BE-031 | Not Started
Integration API | BE-035 | Add integration health check endpoint | GET /api/integrations/{service}/status - test connection | Backend Dev | Medium | 6 | BE-031 | Not Started | Verify token validity

## 3. LLM & Workers
Phase | Task ID | Task Name | Description | Owner/Team | Priority | Estimated Hours | Dependencies | Status | Notes
LLM SERVICE SETUP
LLM Setup | LLM-001 | Set up OpenAI API integration | Configure OpenAI client library with API key management | Backend Dev | Critical | 6 | BE-001 | Not Started | Use environment variables for keys
LLM Setup | LLM-002 | Implement token counting utility | Create function to count tokens using tiktoken library | Backend Dev | High | 4 | LLM-001 | Not Started | For chunk size calculation
LLM Setup | LLM-003 | Design system prompt template | Create prompt instructing LLM to extract tasks in JSON format | ML Engineer | Critical | 12 |  | Not Started | Iterate and test multiple versions
LLM Setup | LLM-004 | Create prompt template with examples | Add few-shot examples to improve extraction accuracy | ML Engineer | High | 8 | LLM-003 | Not Started | Use 3-5 diverse examples
LLM Setup | LLM-005 | Implement LLM client wrapper | Create service class for calling GPT-4 with retry logic | Backend Dev | High | 8 | LLM-001 | Not Started | Include exponential backoff
LLM Setup | LLM-006 | Add LLM response caching | Cache identical prompts to reduce API costs | Backend Dev | Medium | 6 | LLM-005, DB-014 | Not Started | Use Redis with 24h TTL
LLM Setup | LLM-007 | Implement rate limiting for LLM calls | Prevent exceeding OpenAI rate limits | Backend Dev | High | 4 | LLM-005 | Not Started | Track requests per minute
TRANSCRIPT PROCESSING
Processing | LLM-008 | Implement transcript chunking logic | Split long transcripts by speaker turns/paragraphs within token limits | Backend Dev | Critical | 16 | LLM-002 | Not Started | Target 2000 tokens per chunk with overlap
Processing | LLM-009 | Add chunk overlap strategy | Ensure no tasks split across chunk boundaries | Backend Dev | High | 8 | LLM-008 | Not Started | 50-100 token overlap
Processing | LLM-010 | Implement speaker turn detection | Parse transcript to identify speaker changes | Backend Dev | High | 8 | LLM-008 | Not Started | Regex for 'Name:' patterns
Processing | LLM-011 | Create transcript preprocessing pipeline | Clean text: remove filler words, fix encoding, normalize whitespace | Backend Dev | Medium | 6 | LLM-008 | Not Started | Preserve meaning
TASK EXTRACTION
Extraction | LLM-012 | Implement main extraction function | Core function: extractTasks(transcript_text) -> List[Task] | Backend Dev | Critical | 20 | LLM-005, LLM-008 | Not Started | Handle multiple chunks
Extraction | LLM-013 | Implement JSON parsing with validation | Parse LLM output, validate schema, handle malformed JSON | Backend Dev | High | 10 | LLM-012 | Not Started | Use Pydantic for validation
Extraction | LLM-014 | Add fallback for parsing failures | Retry with more explicit prompt if JSON invalid | Backend Dev | High | 8 | LLM-013 | Not Started | Max 2 retries
Extraction | LLM-015 | Implement confidence scoring | Calculate confidence from token log probabilities | ML Engineer | Critical | 20 | LLM-012 | Not Started | Use logprobs API parameter
Extraction | LLM-016 | Create confidence normalization logic | Map raw probabilities to 0-1 confidence score | ML Engineer | High | 8 | LLM-015 | Not Started | Calibrate thresholds
Extraction | LLM-017 | Implement task deduplication | Merge similar/duplicate tasks from multiple chunks | Backend Dev | High | 12 | LLM-012 | Not Started | Use fuzzy string matching
NAME & DATE PARSING
Parsing | LLM-018 | Set up spaCy for NER | Install and configure spaCy for named entity recognition | Backend Dev | High | 6 | BE-001 | Not Started | Use en_core_web_sm model
Parsing | LLM-019 | Implement name-to-user mapping | Match extracted owner names to user database | Backend Dev | Critical | 16 | LLM-018, BE-003 | Not Started | Handle nicknames and partial names
Parsing | LLM-020 | Create participant detection from transcript | Extract all speaker names from transcript header/body | Backend Dev | High | 8 | LLM-010 | Not Started | Build participant list
Parsing | LLM-021 | Implement fuzzy name matching | Use Levenshtein distance for name similarity | Backend Dev | High | 6 | LLM-019 | Not Started | Threshold: 0.8 similarity
Parsing | LLM-022 | Set up dateparser library | Configure natural language date parsing | Backend Dev | High | 4 | BE-001 | Not Started | Handle relative dates
Parsing | LLM-023 | Implement due date parsing | Parse 'next Friday', 'by EOD', etc. to timestamps | Backend Dev | Critical | 12 | LLM-022 | Not Started | Use meeting date as reference
Parsing | LLM-024 | Add timezone handling for dates | Convert parsed dates to UTC considering user timezone | Backend Dev | High | 8 | LLM-023 | Not Started | Use pytz or zoneinfo
Parsing | LLM-025 | Implement ambiguous date resolution | Handle cases like 'Monday' (this week vs next week) | Backend Dev | Medium | 8 | LLM-023 | Not Started | Default to future dates
ERROR HANDLING
Error Handling | LLM-026 | Add timeout handling for LLM calls | Set timeout (30s) and handle gracefully | Backend Dev | High | 4 | LLM-005 | Not Started | Return partial results if available
Error Handling | LLM-027 | Implement fallback to smaller model | Use GPT-3.5-turbo if GPT-4 fails | Backend Dev | Medium | 6 | LLM-005 | Not Started | Log model downgrades
Error Handling | LLM-028 | Add low-confidence task flagging | Auto-flag tasks with confidence <60% for review | Backend Dev | High | 4 | LLM-016 | Not Started | Set status to 'needs_review'
Error Handling | LLM-029 | Create extraction failure alert | Notify user when extraction completely fails | Backend Dev | High | 6 | LLM-012 | Not Started | Provide fallback manual entry
Error Handling | LLM-030 | Log all LLM errors with context | Track prompt, error, chunk, and retry attempts | Backend Dev | High | 4 | LLM-005, SETUP-016 | Not Started | For debugging and monitoring
QUEUE SETUP
Queue Setup | WKR-001 | Choose message queue technology | Decide: RabbitMQ, Redis Queue, AWS SQS, or BullMQ | Tech Lead | Critical | 6 |  | Not Started | Consider hosting and scalability
Queue Setup | WKR-002 | Set up message queue infrastructure | Install and configure chosen queue system | DevOps | Critical | 12 | WKR-001, DB-015 | Not Started
Queue Setup | WKR-003 | Configure Celery workers (if Python) | Set up Celery with Redis/RabbitMQ backend | Backend Dev | High | 10 | WKR-002, BE-001 | Not Started | Or BullMQ for Node.js
Queue Setup | WKR-004 | Implement job queue models | Define job structure: type, payload, status, retries | Backend Dev | High | 6 | WKR-003, DB-006 | Not Started
Queue Setup | WKR-005 | Create job enqueuing utility | Helper function to add jobs to queue from API | Backend Dev | High | 6 | WKR-004 | Not Started
Queue Setup | WKR-006 | Implement job status tracking | Update job status in DB: pending, processing, completed, failed | Backend Dev | High | 8 | WKR-004 | Not Started
Queue Setup | WKR-007 | Add job retry logic | Auto-retry failed jobs with exponential backoff | Backend Dev | High | 8 | WKR-003 | Not Started | Max 3 retries
Queue Setup | WKR-008 | Implement job timeout handling | Kill jobs exceeding max execution time (5 min) | Backend Dev | Medium | 4 | WKR-003 | Not Started
Queue Setup | WKR-009 | Create job result storage | Store job output in DB for API retrieval | Backend Dev | High | 4 | WKR-006 | Not Started
EXTRACTION WORKER
Worker | WKR-010 | Create extraction worker process | Worker to consume extract_tasks jobs from queue | Backend Dev | Critical | 12 | WKR-003, LLM-012 | Not Started
Worker | WKR-011 | Implement task extraction job handler | Process: fetch transcript -> extract tasks -> save to DB | Backend Dev | Critical | 16 | WKR-010, LLM-012 | Not Started
Worker | WKR-012 | Add task confidence filtering | Filter out tasks below minimum confidence threshold | Backend Dev | Medium | 4 | WKR-011, LLM-016 | Not Started | Configurable threshold
Worker | WKR-013 | Implement extraction progress updates | Update job status during chunked processing | Backend Dev | Medium | 6 | WKR-011 | Not Started | Show % complete
Worker | WKR-014 | Add extraction result validation | Validate all required fields present before saving | Backend Dev | High | 6 | WKR-011 | Not Started
Worker | WKR-015 | Create notification trigger | Trigger user notification when extraction completes | Backend Dev | High | 6 | WKR-011 | Not Started | Email or in-app notification
SCHEDULING WORKER
Worker | WKR-016 | Create scheduling worker process | Worker to consume schedule_tasks jobs from queue | Backend Dev | Critical | 12 | WKR-003 | Not Started
Worker | WKR-017 | Implement scheduling job handler | Process: fetch tasks -> get calendar availability -> assign slots | Backend Dev | Critical | 20 | WKR-016, SCHED-001 | Not Started
Worker | WKR-018 | Add scheduling conflict detection | Identify tasks that cannot be scheduled | Backend Dev | High | 10 | WKR-017 | Not Started
Worker | WKR-019 | Implement calendar event creation | Create Google Calendar events for scheduled tasks | Backend Dev | Critical | 12 | WKR-017, INT-003 | Not Started
Worker | WKR-020 | Add scheduling result notification | Notify user of scheduled tasks and conflicts | Backend Dev | High | 6 | WKR-017 | Not Started
INTEGRATION WORKERS
Worker | WKR-021 | Create Slack notification worker | Worker to send Slack messages for completed tasks | Backend Dev | High | 10 | WKR-003, INT-010 | Not Started
Worker | WKR-022 | Create Notion sync worker | Worker to create Notion pages for tasks | Backend Dev | Medium | 10 | WKR-003, INT-015 | Not Started | If Notion integration enabled
Worker | WKR-023 | Implement worker health monitoring | Track worker uptime, job throughput, error rates | DevOps | Medium | 8 | WKR-003 | Not Started
Worker | WKR-024 | Add worker auto-scaling logic | Scale workers based on queue depth | DevOps | Low | 16 | WKR-003, SETUP-013 | Not Started | For production optimization

## 4. Scheduling & Integrations
Phase | Task ID | Task Name | Description | Owner/Team | Priority | Estimated Hours | Dependencies | Status | Notes
SCHEDULING ALGORITHM
Algorithm | SCHED-001 | Design scheduling algorithm | Design earliest-deadline-first greedy algorithm | Tech Lead | Critical | 12 |  | Not Started | Documented in PRD section 4
Algorithm | SCHED-002 | Implement task sorting logic | Sort tasks by deadline, then priority | Backend Dev | High | 6 | SCHED-001 | Not Started
Algorithm | SCHED-003 | Create calendar availability query | Function to get user's free/busy slots from calendar | Backend Dev | Critical | 12 | INT-003 | Not Started
Algorithm | SCHED-004 | Implement free slot detection | Parse calendar response into list of available time blocks | Backend Dev | High | 10 | SCHED-003 | Not Started | Account for buffer time between events
Algorithm | SCHED-005 | Add working hours filtering | Respect user's defined working hours (e.g., 9am-5pm) | Backend Dev | High | 8 | SCHED-004 | Not Started | Store in user preferences
Algorithm | SCHED-006 | Implement timezone conversion | Convert all times to UTC for processing, then back to local | Backend Dev | Critical | 10 | SCHED-004 | Not Started | Use IANA tz database
Algorithm | SCHED-007 | Create greedy slot assignment | Assign each task to earliest fitting slot before deadline | Backend Dev | Critical | 16 | SCHED-004 | Not Started | Core scheduling logic
Algorithm | SCHED-008 | Implement task splitting logic | Split tasks that don't fit in single slot into subtasks | Backend Dev | High | 12 | SCHED-007 | Not Started | Min 30-minute chunks
Algorithm | SCHED-009 | Add conflict detection | Identify tasks that can't be scheduled before deadline | Backend Dev | High | 8 | SCHED-007 | Not Started
Algorithm | SCHED-010 | Implement conflict resolution strategies | Offer options: extend deadline, reduce duration, manual placement | Backend Dev | Medium | 10 | SCHED-009 | Not Started
Algorithm | SCHED-011 | Add duration estimation | Estimate task duration based on description if not provided | ML Engineer | Medium | 12 | SCHED-001 | Not Started | Use simple heuristics or LLM
Algorithm | SCHED-012 | Implement buffer time between tasks | Add 5-15 min buffer between scheduled tasks | Backend Dev | Medium | 4 | SCHED-007 | Not Started | Prevent back-to-back scheduling
Algorithm | SCHED-013 | Add schedule optimization | Optimize for minimal fragmentation of calendar | Backend Dev | Low | 16 | SCHED-007 | Not Started | Future enhancement
CALENDAR MANAGEMENT
Calendar | SCHED-014 | Implement event creation logic | Create calendar event with task details | Backend Dev | Critical | 10 | INT-003 | Not Started | Include task description in event
Calendar | SCHED-015 | Add attendee assignment | Add task owner as attendee to calendar event | Backend Dev | High | 6 | SCHED-014 | Not Started
Calendar | SCHED-016 | Implement event update/reschedule | Allow rescheduling of previously scheduled tasks | Backend Dev | High | 10 | SCHED-014 | Not Started | Update or delete+recreate event
Calendar | SCHED-017 | Add event deletion on task delete | Remove calendar event when task is deleted | Backend Dev | High | 6 | SCHED-014, BE-027 | Not Started
Calendar | SCHED-018 | Implement recurring task handling | Handle tasks that repeat weekly/daily | Backend Dev | Low | 16 | SCHED-014 | Not Started | Future enhancement
Calendar | SCHED-019 | Add custom calendar selection | Let users choose which calendar to use | Backend Dev | Medium | 8 | SCHED-003 | Not Started | Default to primary
EDGE CASES
Edge Cases | SCHED-020 | Handle all-day deadlines | Tasks due 'by end of day' vs specific time | Backend Dev | Medium | 6 | SCHED-007 | Not Started | Default to 5pm local time
Edge Cases | SCHED-021 | Handle past deadlines | Warn or reject tasks with past due dates | Backend Dev | High | 4 | SCHED-007 | Not Started
Edge Cases | SCHED-022 | Handle weekend scheduling | Option to include/exclude weekends from scheduling | Backend Dev | Medium | 6 | SCHED-005 | Not Started | User preference
Edge Cases | SCHED-023 | Handle holiday detection | Respect major holidays in user's region | Backend Dev | Low | 12 | SCHED-005 | Not Started | Use holiday API
Edge Cases | SCHED-024 | Handle DST transitions | Correctly handle daylight saving time changes | Backend Dev | High | 8 | SCHED-006 | Not Started | Critical for accuracy
Edge Cases | SCHED-025 | Handle multi-timezone teams | Schedule for task owner's timezone, not creator's | Backend Dev | Medium | 10 | SCHED-006 | Not Started
GOOGLE CALENDAR
Google | INT-001 | Set up Google Cloud project | Create project and enable Calendar API | DevOps | Critical | 4 |  | Not Started | Configure OAuth consent screen
Google | INT-002 | Configure OAuth 2.0 credentials | Create OAuth client ID and secret for web application | DevOps | Critical | 4 | INT-001 | Not Started | Restrict to authorized domains
Google | INT-003 | Implement Google Calendar client | Create service for interacting with Google Calendar API | Backend Dev | Critical | 12 | INT-002, BE-016 | Not Started | Use official Google client library
Google | INT-004 | Implement calendar list retrieval | Get user's available calendars | Backend Dev | High | 6 | INT-003 | Not Started
Google | INT-005 | Implement events.insert operation | Create calendar events via API | Backend Dev | Critical | 10 | INT-003 | Not Started | Handle API errors
Google | INT-006 | Implement events.list operation | Retrieve calendar events for date range | Backend Dev | High | 8 | INT-003 | Not Started | For free/busy calculation
Google | INT-007 | Implement events.update operation | Update existing calendar events | Backend Dev | High | 8 | INT-003 | Not Started
Google | INT-008 | Implement events.delete operation | Delete calendar events | Backend Dev | High | 6 | INT-003 | Not Started
Google | INT-009 | Add Calendar API rate limiting | Handle quota limits (1M requests/day) | Backend Dev | High | 6 | INT-003 | Not Started | Implement exponential backoff
SLACK
Slack | INT-010 | Create Slack app | Register app at api.slack.com with required scopes | DevOps | High | 4 |  | Not Started | Scopes: chat:write, incoming-webhook
Slack | INT-011 | Configure Slack OAuth | Set up OAuth flow for workspace installation | Backend Dev | High | 8 | INT-010 | Not Started
Slack | INT-012 | Implement Slack client service | Create service for Slack API interactions | Backend Dev | High | 10 | INT-010 | Not Started | Use Slack SDK
Slack | INT-013 | Implement webhook URL storage | Save incoming webhook URL from OAuth response | Backend Dev | High | 4 | INT-011, BE-005 | Not Started
Slack | INT-014 | Create task summary message template | Design Block Kit message showing task list | Backend Dev | High | 8 | INT-012 | Not Started | Include action buttons
Slack | INT-015 | Implement message posting | POST to webhook URL with formatted message | Backend Dev | High | 6 | INT-014 | Not Started
Slack | INT-016 | Add interactive button handlers | Set up endpoint to receive Slack button actions | Backend Dev | Medium | 10 | INT-014 | Not Started | E.g., 'Mark Done' button
Slack | INT-017 | Implement Slack error handling | Handle permission errors, webhook failures | Backend Dev | High | 6 | INT-015 | Not Started | Graceful degradation
NOTION (OPTIONAL)
Notion | INT-018 | Create Notion integration | Register internal integration at notion.so | DevOps | Low | 4 |  | Not Started | If Notion feature enabled
Notion | INT-019 | Implement Notion client service | Create service for Notion API interactions | Backend Dev | Low | 10 | INT-018 | Not Started
Notion | INT-020 | Design task database schema in Notion | Create database with properties for tasks | Backend Dev | Low | 6 | INT-018 | Not Started
Notion | INT-021 | Implement page creation | POST to /v1/pages to create task entries | Backend Dev | Low | 8 | INT-019, INT-020 | Not Started
Notion | INT-022 | Add task status sync | Update Notion pages when task status changes | Backend Dev | Low | 10 | INT-021 | Not Started
LINEAR (OPTIONAL)
Linear | INT-023 | Set up Linear API access | Generate Personal API Key | DevOps | Low | 2 |  | Not Started | If Linear feature enabled
Linear | INT-024 | Implement Linear GraphQL client | Create service for Linear API interactions | Backend Dev | Low | 10 | INT-023 | Not Started
Linear | INT-025 | Implement issue creation mutation | Create Linear issues from tasks | Backend Dev | Low | 10 | INT-024 | Not Started | Map task fields to issue fields
Linear | INT-026 | Add team and project mapping | Let users configure Linear team/project per workspace | Backend Dev | Low | 8 | INT-025 | Not Started
ASANA (OPTIONAL)
Asana | INT-027 | Set up Asana OAuth | Configure OAuth app for Asana integration | DevOps | Low | 4 |  | Not Started | If Asana feature enabled
Asana | INT-028 | Implement Asana client service | Create service for Asana REST API | Backend Dev | Low | 10 | INT-027 | Not Started
Asana | INT-029 | Implement task creation | POST to /tasks endpoint | Backend Dev | Low | 8 | INT-028 | Not Started
Asana | INT-030 | Add workspace and project selection | Let users choose Asana workspace and project | Backend Dev | Low | 8 | INT-029 | Not Started

## 5. Frontend
Phase | Task ID | Task Name | Description | Owner/Team | Priority | Estimated Hours | Dependencies | Status | Notes
FRONTEND SETUP
Frontend Setup | FE-001 | Initialize React project | Create React app with TypeScript using Vite or Next.js | Frontend Dev | Critical | 6 | SETUP-002 | Not Started | Decision: Vite vs Next.js
Frontend Setup | FE-002 | Install UI framework | Set up Material-UI or Ant Design | Frontend Dev | High | 4 | FE-001 | Not Started
Frontend Setup | FE-003 | Configure routing | Set up React Router for SPA navigation | Frontend Dev | High | 6 | FE-001 | Not Started | Routes: /login, /dashboard, /transcripts, /tasks
Frontend Setup | FE-004 | Set up state management | Configure Redux Toolkit or Zustand | Frontend Dev | High | 8 | FE-001 | Not Started | For global state
Frontend Setup | FE-005 | Configure API client | Set up Axios or Fetch wrapper with interceptors | Frontend Dev | High | 8 | FE-001 | Not Started | Include auth token injection
Frontend Setup | FE-006 | Implement authentication context | Create AuthContext for managing auth state | Frontend Dev | High | 10 | FE-004 | Not Started
Frontend Setup | FE-007 | Set up protected route component | Component to redirect unauthenticated users | Frontend Dev | High | 6 | FE-006 | Not Started
Frontend Setup | FE-008 | Configure environment variables | Set up .env for API URLs and feature flags | Frontend Dev | High | 2 | FE-001 | Not Started
Frontend Setup | FE-009 | Set up CSS-in-JS or Tailwind | Choose styling approach and configure | Frontend Dev | Medium | 4 | FE-001 | Not Started | Consider Material-UI's styling
Frontend Setup | FE-010 | Create layout components | Header, Footer, Sidebar, Main container | Frontend Dev | High | 12 | FE-002 | Not Started
AUTHENTICATION PAGES
Auth Pages | FE-011 | Create Login page | Form with email/password, OAuth button, error handling | Frontend Dev | Critical | 12 | FE-003, FE-006 | Not Started
Auth Pages | FE-012 | Create Registration page | Form with email, password, name, timezone selection | Frontend Dev | High | 12 | FE-011 | Not Started
Auth Pages | FE-013 | Implement OAuth login flow | Google OAuth button with redirect handling | Frontend Dev | High | 10 | FE-011, BE-016 | Not Started
Auth Pages | FE-014 | Create Forgot Password page | Email input to request password reset | Frontend Dev | Medium | 8 | FE-011 | Not Started
Auth Pages | FE-015 | Create Reset Password page | New password form with token validation | Frontend Dev | Medium | 8 | FE-014 | Not Started
Auth Pages | FE-016 | Add form validation | Client-side validation for all auth forms | Frontend Dev | High | 6 | FE-011 | Not Started | Use React Hook Form or Formik
DASHBOARD
Dashboard | FE-017 | Create Dashboard page layout | Overview with stats, recent transcripts, upcoming tasks | Frontend Dev | High | 12 | FE-010 | Not Started
Dashboard | FE-018 | Add quick stats widgets | Show: total transcripts, total tasks, tasks this week | Frontend Dev | Medium | 8 | FE-017 | Not Started
Dashboard | FE-019 | Create recent transcripts list | Scrollable list with transcript titles and dates | Frontend Dev | High | 8 | FE-017 | Not Started | Link to transcript detail
Dashboard | FE-020 | Add upcoming tasks widget | List of tasks due soon with confidence badges | Frontend Dev | High | 10 | FE-017 | Not Started
Dashboard | FE-021 | Implement upload transcript button | Prominent CTA to upload new transcript | Frontend Dev | High | 4 | FE-017 | Not Started
TRANSCRIPT MANAGEMENT
Transcripts | FE-022 | Create Transcripts list page | Table/cards showing all user's transcripts | Frontend Dev | High | 12 | FE-003 | Not Started | With pagination
Transcripts | FE-023 | Implement transcript upload modal | File upload or text paste with title input | Frontend Dev | Critical | 16 | FE-022, BE-018 | Not Started | Support .txt, .docx files
Transcripts | FE-024 | Add upload progress indicator | Show progress during file upload and extraction | Frontend Dev | High | 8 | FE-023 | Not Started | WebSocket or polling for job status
Transcripts | FE-025 | Create Transcript detail page | Show transcript text and extracted tasks | Frontend Dev | High | 12 | FE-022 | Not Started
Transcripts | FE-026 | Add transcript search/filter | Search by title, filter by date range | Frontend Dev | Medium | 10 | FE-022 | Not Started
Transcripts | FE-027 | Implement transcript delete | Delete button with confirmation dialog | Frontend Dev | Medium | 6 | FE-022, BE-021 | Not Started
TASK REVIEW INTERFACE
Task Review | FE-028 | Create Task card component | Card showing title, owner, due date, confidence badge | Frontend Dev | Critical | 12 | FE-002 | Not Started | Reusable component
Task Review | FE-029 | Implement confidence badge | Color-coded badge: green ≥85%, yellow 60-84%, red <60% | Frontend Dev | Critical | 8 | FE-028 | Not Started | Match PRD specifications
Task Review | FE-030 | Add confidence tooltip | Hover to see numeric score and explanation | Frontend Dev | High | 6 | FE-029 | Not Started
Task Review | FE-031 | Create inline task editor | Edit title, description, owner, due date inline | Frontend Dev | Critical | 16 | FE-028 | Not Started | Save on blur or button click
Task Review | FE-032 | Implement owner dropdown | Dropdown with participants from transcript | Frontend Dev | High | 10 | FE-031, LLM-020 | Not Started | Allow custom entry
Task Review | FE-033 | Add due date picker | Calendar picker for selecting/editing due date | Frontend Dev | High | 8 | FE-031 | Not Started | Disable past dates
Task Review | FE-034 | Create bulk action toolbar | Checkboxes + toolbar for Accept All, Delete All | Frontend Dev | High | 10 | FE-028 | Not Started
Task Review | FE-035 | Add task filtering by confidence | Tabs or filter to show High/Medium/Low confidence tasks | Frontend Dev | Medium | 8 | FE-028 | Not Started
Task Review | FE-036 | Implement task deletion | Delete button with confirmation | Frontend Dev | High | 6 | FE-028, BE-027 | Not Started
SCHEDULING INTERFACE
Scheduling | FE-037 | Create Scheduling page | Interface for reviewing and scheduling tasks | Frontend Dev | Critical | 16 | FE-003 | Not Started
Scheduling | FE-038 | Add duration input for tasks | Allow users to set estimated duration | Frontend Dev | High | 8 | FE-037 | Not Started | Default suggestions based on task
Scheduling | FE-039 | Implement calendar view component | Weekly calendar grid showing free/busy slots | Frontend Dev | High | 20 | FE-037 | Not Started | Consider using FullCalendar library
Scheduling | FE-040 | Add drag-and-drop scheduling | Drag tasks onto calendar slots | Frontend Dev | Medium | 16 | FE-039 | Not Started | Visual feedback on valid slots
Scheduling | FE-041 | Implement auto-schedule button | Trigger backend scheduling algorithm | Frontend Dev | Critical | 8 | FE-037, BE-028 | Not Started | Show loading state
Scheduling | FE-042 | Display scheduling conflicts | Highlight tasks that couldn't be scheduled | Frontend Dev | High | 10 | FE-037 | Not Started | Show conflict reasons
Scheduling | FE-043 | Add schedule preview | Show planned schedule before confirming | Frontend Dev | High | 10 | FE-037 | Not Started
Scheduling | FE-044 | Implement schedule confirmation | Confirm button to create calendar events | Frontend Dev | High | 8 | FE-043, WKR-019 | Not Started
Scheduling | FE-045 | Add reschedule functionality | Allow rescheduling already-scheduled tasks | Frontend Dev | Medium | 12 | FE-039 | Not Started
SETTINGS & INTEGRATIONS
Settings | FE-046 | Create Settings page | User preferences and integrations management | Frontend Dev | High | 12 | FE-003 | Not Started
Settings | FE-047 | Add profile settings section | Edit name, email, timezone | Frontend Dev | Medium | 8 | FE-046 | Not Started
Settings | FE-048 | Create integrations section | Show connected services with connect/disconnect buttons | Frontend Dev | High | 12 | FE-046 | Not Started
Settings | FE-049 | Implement Google Calendar connect | OAuth flow initiation and status display | Frontend Dev | Critical | 10 | FE-048, INT-002 | Not Started
Settings | FE-050 | Implement Slack connect | OAuth flow for Slack workspace | Frontend Dev | High | 10 | FE-048, INT-011 | Not Started
Settings | FE-051 | Add working hours configuration | Time picker for daily work start/end times | Frontend Dev | High | 10 | FE-046 | Not Started | Per-day customization
Settings | FE-052 | Implement notification preferences | Toggle email/Slack notifications | Frontend Dev | Medium | 8 | FE-046 | Not Started
NOTIFICATIONS & FEEDBACK
UX | FE-053 | Implement toast notifications | Success/error messages for user actions | Frontend Dev | High | 8 | FE-001 | Not Started | Use Snackbar or similar
FE-054 | FE-054 | Add loading states | Spinners/skeletons for all async operations | Frontend Dev | High | 10 | FE-001 | Not Started | Consistent UX
UX | FE-055 | Create error boundary component | Catch and display React errors gracefully | Frontend Dev | High | 6 | FE-001 | Not Started
UX | FE-056 | Implement empty states | Helpful messages when no data exists | Frontend Dev | Medium | 6 | FE-022 | Not Started | Guide users to upload
UX | FE-057 | Add confirmation dialogs | For destructive actions (delete, disconnect) | Frontend Dev | High | 6 | FE-027 | Not Started
RESPONSIVE DESIGN
Responsive | FE-058 | Implement mobile navigation | Hamburger menu for mobile screens | Frontend Dev | Medium | 10 | FE-010 | Not Started
Responsive | FE-059 | Make all pages mobile-responsive | Test and adjust layouts for mobile/tablet | Frontend Dev | High | 20 | FE-058 | Not Started | Breakpoints: 640px, 1024px
Responsive | FE-060 | Optimize touch interactions | Larger tap targets, swipe gestures | Frontend Dev | Low | 8 | FE-059 | Not Started

## 6. Testing & Analytics
Phase | Task ID | Task Name | Description | Owner/Team | Priority | Estimated Hours | Dependencies | Status | Notes
TESTING INFRASTRUCTURE
Test Setup | TEST-001 | Set up backend testing framework | Configure Jest (Node) or Pytest (Python) | Backend Dev | High | 6 | BE-001 | Not Started
Test Setup | TEST-002 | Set up frontend testing framework | Configure Jest + React Testing Library | Frontend Dev | High | 6 | FE-001 | Not Started
Test Setup | TEST-003 | Configure test database | Separate test DB for running tests | Backend Dev | High | 4 | DB-007 | Not Started
Test Setup | TEST-004 | Set up test coverage reporting | Configure coverage tools (pytest-cov, Jest coverage) | DevOps | High | 4 | TEST-001, TEST-002 | Not Started | Target 80% coverage
Test Setup | TEST-005 | Create test data factories | Factory functions/fixtures for creating test data | Backend Dev | High | 10 | TEST-001, BE-003 | Not Started | Use Factory Boy or similar
Test Setup | TEST-006 | Set up API mocking | Mock external APIs (OpenAI, Google, Slack) in tests | Backend Dev | High | 8 | TEST-001 | Not Started | Use nock or responses library
UNIT TESTS - BACKEND
Backend Tests | TEST-007 | Test authentication functions | Unit tests for login, registration, token generation | Backend Dev | High | 12 | BE-010, BE-011, TEST-001 | Not Started
Backend Tests | TEST-008 | Test transcript API endpoints | Test all CRUD operations for transcripts | Backend Dev | High | 16 | BE-018 to BE-023, TEST-001 | Not Started
Backend Tests | TEST-009 | Test task API endpoints | Test all CRUD operations for tasks | Backend Dev | High | 16 | BE-024 to BE-030, TEST-001 | Not Started
Backend Tests | TEST-010 | Test LLM extraction logic | Test task extraction with mocked LLM responses | Backend Dev | High | 20 | LLM-012, TEST-006 | Not Started
Backend Tests | TEST-011 | Test chunking algorithm | Test transcript splitting logic | Backend Dev | Medium | 10 | LLM-008, TEST-001 | Not Started
Backend Tests | TEST-012 | Test name parsing logic | Test name-to-user mapping | Backend Dev | High | 12 | LLM-019, TEST-001 | Not Started
Backend Tests | TEST-013 | Test date parsing logic | Test natural language date conversion | Backend Dev | High | 12 | LLM-023, TEST-001 | Not Started | Include edge cases
Backend Tests | TEST-014 | Test scheduling algorithm | Test slot assignment logic | Backend Dev | Critical | 20 | SCHED-007, TEST-001 | Not Started | Multiple scenarios
Backend Tests | TEST-015 | Test calendar integration | Test Google Calendar API calls | Backend Dev | High | 12 | INT-003, TEST-006 | Not Started
Backend Tests | TEST-016 | Test worker job handlers | Test extraction and scheduling workers | Backend Dev | High | 16 | WKR-011, WKR-017, TEST-001 | Not Started
UNIT TESTS - FRONTEND
Frontend Tests | TEST-017 | Test authentication components | Test Login, Register pages | Frontend Dev | High | 12 | FE-011, FE-012, TEST-002 | Not Started
Frontend Tests | TEST-018 | Test Task card component | Test rendering, editing, confidence badges | Frontend Dev | High | 10 | FE-028, TEST-002 | Not Started
Frontend Tests | TEST-019 | Test transcript upload flow | Test file upload, validation, progress | Frontend Dev | High | 12 | FE-023, TEST-002 | Not Started
Frontend Tests | TEST-020 | Test scheduling interface | Test calendar view, drag-drop | Frontend Dev | Medium | 16 | FE-039, FE-040, TEST-002 | Not Started
Frontend Tests | TEST-021 | Test form validation | Test all form inputs and error states | Frontend Dev | High | 10 | FE-016, TEST-002 | Not Started
INTEGRATION TESTS
Integration | TEST-022 | Test end-to-end transcript flow | Upload → Extract → Review → Schedule → Calendar | QA | Critical | 20 | BE-018, LLM-012, SCHED-007, INT-005 | Not Started | Full happy path
Integration | TEST-023 | Test OAuth flows | Test Google and Slack OAuth complete flow | QA | High | 12 | BE-016, INT-011 | Not Started
Integration | TEST-024 | Test worker processing | Test async job queue end-to-end | QA | High | 16 | WKR-011, WKR-017 | Not Started
Integration | TEST-025 | Test API error handling | Test all error scenarios (401, 404, 500, etc.) | QA | High | 12 | BE-007 | Not Started
Integration | TEST-026 | Test calendar sync | Test task scheduling creates correct calendar events | QA | Critical | 12 | SCHED-014, INT-005 | Not Started
E2E TESTS
E2E | TEST-027 | Set up E2E testing framework | Configure Playwright or Cypress | QA | High | 8 | FE-001 | Not Started
E2E | TEST-028 | Create E2E test for user registration | Complete signup flow | QA | High | 8 | TEST-027, FE-012 | Not Started
E2E | TEST-029 | Create E2E test for transcript upload | Login → Upload → View tasks | QA | Critical | 12 | TEST-027, FE-023 | Not Started
E2E | TEST-030 | Create E2E test for task editing | Edit task details and save | QA | High | 8 | TEST-027, FE-031 | Not Started
E2E | TEST-031 | Create E2E test for scheduling | Schedule tasks and verify calendar events | QA | Critical | 16 | TEST-027, FE-041 | Not Started
E2E | TEST-032 | Test mobile responsive flows | Run E2E tests on mobile viewport | QA | Medium | 10 | TEST-027, FE-059 | Not Started
ANALYTICS SETUP
Analytics | ANLYT-001 | Choose analytics platform | Decide: PostHog, Mixpanel, or Amplitude | Product Manager | High | 4 |  | Not Started | Consider budget and features
Analytics | ANLYT-002 | Set up analytics SDK | Install and configure chosen analytics library | Frontend Dev | High | 6 | ANLYT-001, FE-001 | Not Started
Analytics | ANLYT-003 | Implement event tracking helper | Create wrapper function for consistent event tracking | Frontend Dev | High | 6 | ANLYT-002 | Not Started
Analytics | ANLYT-004 | Add user identification | Track user ID on login/signup | Frontend Dev | High | 4 | ANLYT-002, FE-011 | Not Started
USER EVENTS
Events | ANLYT-005 | Track transcript_uploaded event | Fire when user uploads transcript | Frontend Dev | High | 4 | ANLYT-003, FE-023 | Not Started | Payload: word_count, source
Events | ANLYT-006 | Track tasks_extracted event | Fire when LLM extraction completes | Backend Dev | High | 4 | ANLYT-003, WKR-011 | Not Started | Payload: num_tasks, extraction_time_ms
Events | ANLYT-007 | Track task_reviewed event | Fire when user edits/deletes task | Frontend Dev | High | 4 | ANLYT-003, FE-031 | Not Started | Payload: action, confidence
Events | ANLYT-008 | Track tasks_scheduled event | Fire when scheduling completes | Backend Dev | High | 4 | ANLYT-003, WKR-017 | Not Started | Payload: success, num_conflicts
Events | ANLYT-009 | Track integration_clicked event | Fire when user connects integration | Frontend Dev | High | 4 | ANLYT-003, FE-049 | Not Started | Payload: service, outcome
Events | ANLYT-010 | Track page views | Automatically track all route changes | Frontend Dev | Medium | 4 | ANLYT-002, FE-003 | Not Started
Events | ANLYT-011 | Track feature usage | Track usage of key features (filters, search, etc.) | Frontend Dev | Medium | 8 | ANLYT-003 | Not Started
SYSTEM METRICS
Metrics | ANLYT-012 | Set up Prometheus | Install and configure Prometheus for metrics | DevOps | Medium | 10 | SETUP-013 | Not Started | Or use cloud provider metrics
Metrics | ANLYT-013 | Add API latency metrics | Track response times for all endpoints | Backend Dev | High | 8 | ANLYT-012, BE-008 | Not Started
Metrics | ANLYT-014 | Add LLM call metrics | Track LLM latency, token usage, error rates | Backend Dev | High | 8 | ANLYT-012, LLM-005 | Not Started
Metrics | ANLYT-015 | Add database query metrics | Track slow queries and connection pool | Backend Dev | Medium | 6 | ANLYT-012, DB-011 | Not Started
Metrics | ANLYT-016 | Add queue metrics | Track queue depth, job throughput, failures | Backend Dev | High | 8 | ANLYT-012, WKR-006 | Not Started
Metrics | ANLYT-017 | Set up alerting | Create alerts for critical metrics (error rate, downtime) | DevOps | High | 10 | ANLYT-012 | Not Started | PagerDuty or similar
DASHBOARDS
Dashboards | ANLYT-018 | Create user analytics dashboard | Funnel analysis, retention, feature usage | Product Manager | Medium | 12 | ANLYT-001 | Not Started
Dashboards | ANLYT-019 | Create system health dashboard | API latency, error rates, uptime | DevOps | High | 10 | ANLYT-012 | Not Started | Grafana or similar
Dashboards | ANLYT-020 | Create LLM performance dashboard | Extraction accuracy, confidence distribution | ML Engineer | Medium | 10 | ANLYT-014 | Not Started

## 7. Security & Documentation
Phase | Task ID | Task Name | Description | Owner/Team | Priority | Estimated Hours | Dependencies | Status | Notes
SECURITY FUNDAMENTALS
Security | SEC-001 | Implement password hashing | Use bcrypt or Argon2 for password storage | Backend Dev | Critical | 6 | BE-010 | Not Started | Never store plaintext passwords
Security | SEC-002 | Add rate limiting | Rate limit API endpoints (login, registration, LLM calls) | Backend Dev | Critical | 10 | BE-001 | Not Started | Prevent brute force attacks
Security | SEC-003 | Implement CSRF protection | Add CSRF tokens to all state-changing requests | Backend Dev | High | 6 | BE-001 | Not Started
Security | SEC-004 | Configure secure headers | Set CSP, HSTS, X-Frame-Options, etc. | Backend Dev | High | 4 | BE-001 | Not Started | Use helmet.js or similar
Security | SEC-005 | Add input validation and sanitization | Validate and sanitize all user inputs | Backend Dev | Critical | 12 | BE-005 | Not Started | Prevent XSS and injection
Security | SEC-006 | Implement SQL injection prevention | Use parameterized queries everywhere | Backend Dev | Critical | 8 | BE-002 | Not Started | ORM should handle this
Security | SEC-007 | Add XSS protection | Sanitize output, use Content-Security-Policy | Backend Dev | Critical | 8 | BE-001 | Not Started
Security | SEC-008 | Implement request size limits | Limit request body size to prevent DoS | Backend Dev | High | 4 | BE-001 | Not Started | E.g., 10MB max
DATA PROTECTION
Data Protection | SEC-009 | Implement database encryption at rest | Encrypt sensitive DB fields (tokens, passwords) | DevOps | Critical | 10 | DB-007 | Not Started | Use DB encryption features
Data Protection | SEC-010 | Add TLS/SSL for data in transit | Configure HTTPS with valid certificates | DevOps | Critical | 8 | SETUP-013 | Not Started | Use Let's Encrypt
Data Protection | SEC-011 | Implement token encryption | Encrypt OAuth tokens before DB storage | Backend Dev | Critical | 8 | BE-005 | Not Started | Use AES-256
Data Protection | SEC-012 | Add secrets management | Use secure vault for API keys and secrets | DevOps | Critical | 10 | SETUP-015 | Not Started | AWS Secrets Manager or similar
Data Protection | SEC-013 | Implement data retention policy | Auto-delete old transcripts and tasks | Backend Dev | Medium | 8 | DB-001 | Not Started | Configurable retention period
Data Protection | SEC-014 | Add user data export | Allow users to download their data (GDPR) | Backend Dev | High | 12 | BE-004 | Not Started | JSON export of all user data
Data Protection | SEC-015 | Implement account deletion | Complete data deletion on account close | Backend Dev | High | 10 | BE-004 | Not Started | Cascade delete all related data
AUTHENTICATION SECURITY
Auth Security | SEC-016 | Implement session timeout | Auto-logout after inactivity period | Backend Dev | High | 6 | BE-014 | Not Started | 30 min default
Auth Security | SEC-017 | Add multi-factor authentication (MFA) | Support TOTP or SMS-based 2FA | Backend Dev | Medium | 20 | BE-011 | Not Started | Future enhancement
Auth Security | SEC-018 | Implement login attempt logging | Log all login attempts (success and failure) | Backend Dev | High | 6 | BE-011, SETUP-016 | Not Started | For security auditing
Auth Security | SEC-019 | Add account lockout | Lock account after N failed login attempts | Backend Dev | High | 8 | BE-011 | Not Started | 5 attempts, 15 min lockout
Auth Security | SEC-020 | Implement secure password reset | Time-limited tokens, invalidate after use | Backend Dev | High | 8 | BE-013 | Not Started
COMPLIANCE
Compliance | SEC-021 | Create privacy policy | Draft comprehensive privacy policy | Legal | High | 12 |  | Not Started | Required for GDPR compliance
Compliance | SEC-022 | Create terms of service | Draft terms of service document | Legal | High | 12 |  | Not Started
Compliance | SEC-023 | Add cookie consent banner | GDPR-compliant cookie consent | Frontend Dev | High | 8 | FE-001 | Not Started | If using non-essential cookies
Compliance | SEC-024 | Implement GDPR data processing agreement | For users in EU | Legal | Medium | 8 |  | Not Started | If targeting EU users
Compliance | SEC-025 | Add audit logging | Log all data access and modifications | Backend Dev | Medium | 12 | BE-001 | Not Started | For compliance auditing
API DOCUMENTATION
API Docs | DOC-001 | Set up API documentation tool | Configure Swagger/OpenAPI or similar | Backend Dev | High | 6 | BE-001 | Not Started | Auto-generate from code
API Docs | DOC-002 | Document authentication endpoints | Document /auth/* endpoints with examples | Backend Dev | High | 8 | BE-009 to BE-017, DOC-001 | Not Started
API Docs | DOC-003 | Document transcript endpoints | Document all transcript CRUD endpoints | Backend Dev | High | 8 | BE-018 to BE-023, DOC-001 | Not Started
API Docs | DOC-004 | Document task endpoints | Document all task endpoints | Backend Dev | High | 8 | BE-024 to BE-030, DOC-001 | Not Started
API Docs | DOC-005 | Document integration endpoints | Document OAuth and integration management | Backend Dev | High | 6 | BE-031 to BE-035, DOC-001 | Not Started
API Docs | DOC-006 | Add request/response examples | Provide example payloads for all endpoints | Backend Dev | High | 10 | DOC-001 | Not Started
API Docs | DOC-007 | Document error responses | List all possible error codes and messages | Backend Dev | High | 6 | DOC-001 | Not Started
API Docs | DOC-008 | Create GraphQL schema documentation | If using GraphQL, document schema | Backend Dev | Medium | 8 | BE-004, DOC-001 | Not Started
TECHNICAL DOCUMENTATION
Tech Docs | DOC-009 | Write architecture overview | High-level system architecture document | Tech Lead | High | 16 |  | Not Started | Include diagrams
Tech Docs | DOC-010 | Document database schema | ERD and table descriptions | Backend Dev | High | 8 | DB-001 | Not Started
Tech Docs | DOC-011 | Create deployment guide | Step-by-step deployment instructions | DevOps | High | 12 | SETUP-014 | Not Started
Tech Docs | DOC-012 | Write local development setup guide | Instructions for setting up dev environment | Tech Lead | High | 10 | SETUP-005 | Not Started
Tech Docs | DOC-013 | Document LLM prompt engineering | Explain prompt templates and tuning process | ML Engineer | Medium | 8 | LLM-003 | Not Started
Tech Docs | DOC-014 | Document scheduling algorithm | Explain slot-finding logic and edge cases | Backend Dev | Medium | 10 | SCHED-001 | Not Started
Tech Docs | DOC-015 | Create troubleshooting guide | Common issues and solutions | Tech Lead | Medium | 12 |  | Not Started
USER DOCUMENTATION
User Docs | DOC-016 | Write user onboarding guide | Getting started guide for new users | Product Manager | High | 12 |  | Not Started
User Docs | DOC-017 | Create video tutorials | Screen recordings for key workflows | Product Manager | Medium | 20 |  | Not Started | Upload, review, schedule
User Docs | DOC-018 | Write FAQ document | Common questions and answers | Product Manager | Medium | 8 |  | Not Started
User Docs | DOC-019 | Create integration guides | How to connect Google, Slack, etc. | Product Manager | High | 10 | INT-003, INT-012 | Not Started
User Docs | DOC-020 | Add in-app tooltips | Contextual help throughout the UI | Frontend Dev | Medium | 12 | FE-030 | Not Started | Use onboarding library
CODE DOCUMENTATION
Code Docs | DOC-021 | Add JSDoc/docstrings | Document all functions and classes | All Devs | Medium | 20 |  | Not Started | Ongoing during development
Code Docs | DOC-022 | Create contributing guide | Guidelines for contributing to codebase | Tech Lead | Low | 6 | SETUP-001 | Not Started
Code Docs | DOC-023 | Document code style guide | Coding standards and conventions | Tech Lead | Low | 6 | SETUP-006 | Not Started

## 8. Deploy & Launch
Phase | Task ID | Task Name | Description | Owner/Team | Priority | Estimated Hours | Dependencies | Status | Notes
HOSTING INFRASTRUCTURE
Infrastructure | DEPLOY-001 | Choose hosting providers | Finalize: Frontend (Vercel/Netlify), Backend (Render/Fly.io), DB (Supabase/RDS) | Tech Lead | Critical | 8 |  | Not Started | Consider cost and scalability
Infrastructure | DEPLOY-002 | Set up production database | Create production PostgreSQL instance | DevOps | Critical | 10 | DEPLOY-001, DB-007 | Not Started | Enable automated backups
Infrastructure | DEPLOY-003 | Set up Redis production instance | Create production Redis for queue and cache | DevOps | Critical | 6 | DEPLOY-001, DB-014 | Not Started
Infrastructure | DEPLOY-004 | Configure CDN | Set up CDN for frontend static assets | DevOps | High | 6 | DEPLOY-001 | Not Started | CloudFlare or similar
Infrastructure | DEPLOY-005 | Set up object storage | Create S3 bucket or equivalent for media files | DevOps | High | 4 | DEPLOY-001, DB-013 | Not Started
Infrastructure | DEPLOY-006 | Configure DNS | Set up custom domain and DNS records | DevOps | High | 4 | DEPLOY-001 | Not Started
Infrastructure | DEPLOY-007 | Set up SSL certificates | Configure HTTPS with auto-renewal | DevOps | Critical | 6 | DEPLOY-006 | Not Started | Let's Encrypt
CONTAINERIZATION
Containers | DEPLOY-008 | Create production Dockerfile for backend | Optimize for size and security | DevOps | High | 8 | BE-001 | Not Started | Multi-stage build
Containers | DEPLOY-009 | Create production Dockerfile for workers | Separate image for worker processes | DevOps | High | 6 | WKR-003 | Not Started
Containers | DEPLOY-010 | Create docker-compose for production | Production-ready compose file | DevOps | Medium | 6 | DEPLOY-008 | Not Started | Or use orchestration
Containers | DEPLOY-011 | Set up container registry | Docker Hub, ECR, or GCR | DevOps | High | 4 | DEPLOY-008 | Not Started
Containers | DEPLOY-012 | Configure health checks | Container health check endpoints | Backend Dev | High | 6 | BE-001 | Not Started | GET /health
DEPLOYMENT AUTOMATION
Automation | DEPLOY-013 | Create staging deployment workflow | Automated deploy to staging on merge to develop | DevOps | High | 12 | SETUP-013 | Not Started
Automation | DEPLOY-014 | Create production deployment workflow | Automated deploy to prod on merge to main | DevOps | High | 16 | DEPLOY-013 | Not Started | Require manual approval
Automation | DEPLOY-015 | Implement database migration in CI/CD | Auto-run migrations on deployment | DevOps | High | 8 | DB-008, DEPLOY-014 | Not Started
Automation | DEPLOY-016 | Add deployment rollback mechanism | Quick rollback for failed deployments | DevOps | High | 10 | DEPLOY-014 | Not Started
Automation | DEPLOY-017 | Configure auto-scaling | Scale backend/workers based on load | DevOps | Medium | 16 | DEPLOY-001 | Not Started | Use platform auto-scaling
Automation | DEPLOY-018 | Set up blue-green deployment | Zero-downtime deployment strategy | DevOps | Low | 20 | DEPLOY-014 | Not Started | Future optimization
ENVIRONMENT CONFIGURATION
Config | DEPLOY-019 | Set production environment variables | Configure all required env vars for production | DevOps | Critical | 8 | DEPLOY-002 | Not Started | OpenAI key, DB URL, OAuth creds
Config | DEPLOY-020 | Configure production logging | Set appropriate log levels and retention | DevOps | High | 6 | SETUP-016, DEPLOY-002 | Not Started | Ship logs to centralized service
Config | DEPLOY-021 | Set up backup and disaster recovery | Automated backups with restore testing | DevOps | Critical | 12 | DEPLOY-002 | Not Started | Test restore quarterly
Config | DEPLOY-022 | Configure rate limits for production | Set production-appropriate rate limits | DevOps | High | 4 | SEC-002, DEPLOY-002 | Not Started
Config | DEPLOY-023 | Set up monitoring alerts | Configure alerts for production issues | DevOps | Critical | 10 | ANLYT-017, DEPLOY-002 | Not Started | Email/SMS/Slack
PERFORMANCE OPTIMIZATION
Performance | OPT-001 | Add database query optimization | Analyze and optimize slow queries | Backend Dev | Medium | 16 | DB-009 | Not Started | Use EXPLAIN ANALYZE
Performance | OPT-002 | Implement API response caching | Cache frequent GET requests | Backend Dev | Medium | 10 | DB-014 | Not Started | Redis cache with TTL
Performance | OPT-003 | Add database connection pooling optimization | Tune pool size for load | Backend Dev | Medium | 6 | DB-011 | Not Started
Performance | OPT-004 | Optimize LLM token usage | Reduce unnecessary tokens in prompts | ML Engineer | Medium | 8 | LLM-003 | Not Started | Reduce API costs
Performance | OPT-005 | Implement lazy loading in frontend | Load components and images on demand | Frontend Dev | Medium | 12 | FE-001 | Not Started | React.lazy and Suspense
Performance | OPT-006 | Add frontend code splitting | Split bundles by route | Frontend Dev | Medium | 8 | FE-003 | Not Started | Reduce initial load time
Performance | OPT-007 | Optimize frontend bundle size | Tree shaking, minification, compression | Frontend Dev | Medium | 10 | FE-001 | Not Started | Target <500KB initial load
Performance | OPT-008 | Add image optimization | Compress and lazy-load images | Frontend Dev | Low | 6 | FE-001 | Not Started | Use WebP format
Performance | OPT-009 | Implement API pagination | Add pagination to all list endpoints | Backend Dev | High | 12 | BE-019, BE-029 | Not Started | Default page size 20
Performance | OPT-010 | Add database indexing strategy | Create indexes based on query patterns | Backend Dev | High | 12 | DB-009 | Not Started | Monitor index usage
SCALABILITY
Scalability | OPT-011 | Implement horizontal scaling for workers | Allow multiple worker instances | DevOps | Medium | 12 | WKR-003 | Not Started
Scalability | OPT-012 | Add load balancer | Distribute traffic across backend instances | DevOps | Low | 16 | DEPLOY-017 | Not Started | Use platform load balancer
Scalability | OPT-013 | Implement job queue partitioning | Separate queues for different job types | Backend Dev | Low | 10 | WKR-001 | Not Started | Priority queues
Scalability | OPT-014 | Add database sharding strategy | Plan for horizontal database scaling | Tech Lead | Low | 20 | DB-001 | Not Started | Future optimization
PRE-LAUNCH
Pre-Launch | LAUNCH-001 | Conduct security audit | Third-party security assessment | Security Team | Critical | 40 | SEC-001 to SEC-025 | Not Started | Identify vulnerabilities
Pre-Launch | LAUNCH-002 | Perform load testing | Test system under expected peak load | QA | Critical | 20 | TEST-001, DEPLOY-002 | Not Started | Use k6 or similar
Pre-Launch | LAUNCH-003 | Conduct penetration testing | Ethical hacking to find vulnerabilities | Security Team | High | 40 | SEC-001, DEPLOY-002 | Not Started
Pre-Launch | LAUNCH-004 | Create incident response plan | Document procedures for handling incidents | Tech Lead | High | 12 |  | Not Started
Pre-Launch | LAUNCH-005 | Set up customer support system | Email support or helpdesk software | Product Manager | High | 8 |  | Not Started | Zendesk, Intercom, or similar
Pre-Launch | LAUNCH-006 | Create launch checklist | Final pre-launch verification checklist | Tech Lead | High | 8 |  | Not Started
Pre-Launch | LAUNCH-007 | Conduct UAT (User Acceptance Testing) | Beta testing with select users | Product Manager | Critical | 40 | TEST-027 to TEST-032 | Not Started | Gather feedback
Pre-Launch | LAUNCH-008 | Prepare marketing materials | Landing page, screenshots, demo video | Marketing | High | 40 | FE-059 | Not Started
BETA LAUNCH
Beta | LAUNCH-009 | Deploy to beta environment | Limited release to beta testers | DevOps | High | 8 | DEPLOY-014, LAUNCH-007 | Not Started
Beta | LAUNCH-010 | Monitor beta metrics closely | Track errors, performance, user feedback | Product Manager | High | 20 | ANLYT-018, LAUNCH-009 | Not Started | Daily monitoring
Beta | LAUNCH-011 | Collect and prioritize beta feedback | Create issues from user feedback | Product Manager | High | 20 | LAUNCH-010 | Not Started
Beta | LAUNCH-012 | Fix critical beta issues | Address showstopper bugs | All Devs | Critical | 80 | LAUNCH-011 | Not Started | Before public launch
PUBLIC LAUNCH
Launch | LAUNCH-013 | Final production deployment | Deploy stable version to production | DevOps | Critical | 8 | LAUNCH-012, DEPLOY-014 | Not Started
Launch | LAUNCH-014 | Activate monitoring and alerts | Ensure all monitoring is active | DevOps | Critical | 4 | ANLYT-017, LAUNCH-013 | Not Started
Launch | LAUNCH-015 | Publish marketing announcement | Blog post, social media, press release | Marketing | High | 16 | LAUNCH-013 | Not Started
Launch | LAUNCH-016 | Submit to directories | Product Hunt, BetaList, etc. | Marketing | Medium | 8 | LAUNCH-015 | Not Started
Launch | LAUNCH-017 | Monitor launch day metrics | Watch for issues, track signups | All | Critical | 16 | LAUNCH-013 | Not Started | War room monitoring
POST-LAUNCH
Post-Launch | LAUNCH-018 | Establish on-call rotation | 24/7 coverage for critical issues | DevOps | High | 8 | LAUNCH-013 | Not Started
Post-Launch | LAUNCH-019 | Create user feedback loop | In-app feedback mechanism | Product Manager | High | 12 | FE-001 | Not Started
Post-Launch | LAUNCH-020 | Plan feature roadmap | Prioritize next features based on feedback | Product Manager | High | 20 | LAUNCH-011 | Not Started

## 9. Future Enhancements
Phase | Task ID | Task Name | Description | Owner/Team | Priority | Estimated Hours | Dependencies | Status | Notes
ADVANCED FEATURES
Advanced | FUTURE-001 | Add multi-language support | i18n for multiple languages | Frontend Dev | Low | 40 | FE-001 | Not Started | Start with Spanish, French
Advanced | FUTURE-002 | Implement voice-to-text transcription | Upload audio/video, auto-transcribe | Backend Dev | Medium | 40 | BE-018 | Not Started | Use Whisper API or similar
Advanced | FUTURE-003 | Add real-time collaboration | Multiple users editing tasks simultaneously | Backend Dev | Low | 60 | BE-024 | Not Started | WebSocket-based
Advanced | FUTURE-004 | Implement task dependencies | Define task order and prerequisites | Backend Dev | Low | 30 | DB-004, SCHED-001 | Not Started | Affects scheduling
Advanced | FUTURE-005 | Add recurring tasks support | Tasks that repeat on schedule | Backend Dev | Low | 40 | DB-004, SCHED-018 | Not Started
Advanced | FUTURE-006 | Implement task templates | Pre-defined task sets for common meetings | Backend Dev | Low | 20 | DB-001 | Not Started | E.g., 'Sprint Planning' template
Advanced | FUTURE-007 | Add team/workspace support | Multiple users in shared workspace | Backend Dev | Medium | 80 | DB-002 | Not Started | Major feature
Advanced | FUTURE-008 | Implement task prioritization | User-defined priority levels | Backend Dev | Low | 15 | DB-004 | Not Started | Affects scheduling order
Advanced | FUTURE-009 | Add email integration | Extract tasks from emails | Backend Dev | Low | 60 | LLM-012 | Not Started | Gmail/Outlook integration
Advanced | FUTURE-010 | Implement smart suggestions | Suggest optimal meeting times based on history | ML Engineer | Low | 40 | SCHED-001 | Not Started | ML-based
INTEGRATIONS EXPANSION
Integrations | FUTURE-011 | Add Microsoft Teams integration | Similar to Slack integration | Backend Dev | Low | 40 | INT-010 | Not Started
Integrations | FUTURE-012 | Add Zoom integration | Auto-fetch transcripts from Zoom meetings | Backend Dev | Low | 50 | BE-018 | Not Started | Zoom API + webhooks
Integrations | FUTURE-013 | Add Microsoft Outlook Calendar | Alternative to Google Calendar | Backend Dev | Medium | 40 | INT-003 | Not Started
Integrations | FUTURE-014 | Add Jira integration | Create Jira tickets from tasks | Backend Dev | Low | 30 | INT-023 | Not Started
Integrations | FUTURE-015 | Add Trello integration | Create Trello cards from tasks | Backend Dev | Low | 30 | INT-023 | Not Started
Integrations | FUTURE-016 | Add Monday.com integration | Sync tasks to Monday boards | Backend Dev | Low | 30 | INT-023 | Not Started
MOBILE APPLICATION
Mobile | FUTURE-017 | Design mobile app architecture | Native vs React Native vs Flutter | Tech Lead | Low | 20 |  | Not Started
Mobile | FUTURE-018 | Develop iOS app | Native iOS application | Mobile Dev | Low | 300 | FUTURE-017 | Not Started
Mobile | FUTURE-019 | Develop Android app | Native Android application | Mobile Dev | Low | 300 | FUTURE-017 | Not Started
Mobile | FUTURE-020 | Add push notifications | Mobile push for task reminders | Mobile Dev | Low | 40 | FUTURE-018 | Not Started
AI/ML ENHANCEMENTS
AI/ML | FUTURE-021 | Fine-tune custom extraction model | Train model on user feedback | ML Engineer | Low | 100 | LLM-015 | Not Started | Improve accuracy
AI/ML | FUTURE-022 | Add sentiment analysis | Detect urgency/priority from tone | ML Engineer | Low | 40 | LLM-012 | Not Started
AI/ML | FUTURE-023 | Implement action item categorization | Auto-categorize tasks by type | ML Engineer | Low | 30 | LLM-012 | Not Started
AI/ML | FUTURE-024 | Add task estimation ML model | Better duration predictions | ML Engineer | Low | 60 | SCHED-011 | Not Started
AI/ML | FUTURE-025 | Implement meeting summarization | Auto-generate meeting summaries | ML Engineer | Low | 40 | LLM-012 | Not Started